## Dashboard
TopDog Codebase Improvement Plan
Generated: January 25, 2026
| Total Tasks | Completed |  | In Progress | Not Started
Overall Progress
| Tasks by Priority |  | Tasks by Category
| P0 (Critical) |  | Performance
| P1 (High) |  | Code Quality
| P2 (Medium) |  | Architecture
| P3 (Low) |  | Security

## Task List
Task ID | Task Description | Priority | Category | Effort (hrs) | Due Date | Status | Assigned To | Notes
T001 | Convert large PNGs to WebP format (do_riding_football_III.png - 6.4MB) | P0 | Performance | 2 | 2026-02-01 | Not Started |  | Use: cwebp -q 80 input.png -o output.webp
T002 | Convert dog_no_background.png to WebP (5.9MB) | P0 | Performance | 1 | 2026-02-01 | Not Started |  | Same compression settings
T003 | Convert do_riding_football_II.png to WebP (5.0MB) | P0 | Performance | 1 | 2026-02-01 | Not Started |  | Same compression settings
T004 | Convert !!_GLOBE_NOBACKGROUND.png to WebP (4.7MB) | P0 | Performance | 1 | 2026-02-01 | Not Started |  | Same compression settings
T005 | Add React.memo() to DraftStatusBar component | P0 | Performance | 1 | 2026-02-01 | Not Started |  | components/vx2/draft-room/components/DraftStatusBar.tsx
T006 | Add React.memo() to PicksBar component | P0 | Performance | 1 | 2026-02-01 | Not Started |  | components/vx2/draft-room/components/PicksBar.tsx
T007 | Add React.memo() to PlayerList component | P0 | Performance | 1 | 2026-02-01 | Not Started |  | components/vx2/draft-room/components/PlayerList.tsx
T008 | Add React.memo() to QueueView, RosterView, DraftBoard | P0 | Performance | 2 | 2026-02-01 | Not Started |  | Batch these together
T009 | Remove console.log statements from lib/firebase.ts | P1 | Code Quality | 2 | 2026-02-08 | Not Started |  | 14+ console statements identified
T010 | Remove console statements from functions/src/draftTriggers.ts | P1 | Code Quality | 2 | 2026-02-08 | Not Started |  | Draft trigger logging
T011 | Remove console statements from lib/stripe/stripeService.ts | P1 | Code Quality | 1 | 2026-02-08 | Not Started |  | Payment debugging logs
T012 | Audit and remove remaining 550+ console statements | P1 | Code Quality | 8 | 2026-02-08 | Not Started |  | Run: grep -r 'console\.' --include='*.ts' --include='*.tsx'
T013 | Fix TypeScript 'any' types in useDraftPicks.ts | P1 | Code Quality | 3 | 2026-02-08 | Not Started |  | convertFirebasePick uses any
T014 | Fix TypeScript 'any' types in queryOptimization.ts | P1 | Code Quality | 2 | 2026-02-08 | Not Started |  | Multiple any in query options
T015 | Fix TypeScript 'any' types in draftTriggers.ts | P1 | Code Quality | 2 | 2026-02-08 | Not Started |  | (p: any) => patterns
T016 | Fix TypeScript 'any' types in fcmService.ts | P1 | Code Quality | 1 | 2026-02-08 | Not Started |  | callback: (payload: any)
T017 | Resolve TODO: Implement notable events detection | P1 | Code Quality | 4 | 2026-02-08 | Not Started |  | slow-drafts/index.ts
T018 | Resolve TODO: Convert to USD equivalent for balance check | P1 | Code Quality | 3 | 2026-02-08 | Not Started |  | paystackService.ts - critical for payments
T019 | Resolve TODO: Save for future if requested | P1 | Code Quality | 2 | 2026-02-08 | Not Started |  | xendit/disbursement.ts
T020 | Add Cache-Control headers to player pool endpoints | P1 | Performance | 2 | 2026-02-08 | Not Started |  | lib/playerPool/usePlayerPool.ts
T021 | Add Cache-Control headers to display-currency endpoint | P1 | Performance | 1 | 2026-02-08 | Not Started |  | pages/api/user/display-currency.ts
T022 | Replace fetch() with useSWR() in useDisplayCurrency | P1 | Performance | 3 | 2026-02-08 | Not Started |  | Request deduplication
T023 | Ensure VirtualizedPlayerList is default for player rendering | P1 | Performance | 2 | 2026-02-08 | Not Started |  | Check if PlayerList or VirtualizedPlayerList is used
T024 | Refactor lib/sportsdataio.ts (2,201 lines) | P2 | Architecture | 8 | 2026-02-24 | Not Started |  | Split by data type (players, teams, games)
T025 | Refactor lib/userMetrics.ts (1,296 lines) | P2 | Architecture | 6 | 2026-02-24 | Not Started |  | Extract metric categories into modules
T026 | Refactor lib/vipAccountManager.ts (1,132 lines) | P2 | Architecture | 6 | 2026-02-24 | Not Started |  | 14 duplicate Firebase checks to extract
T027 | Extract common patterns from payment services | P2 | Architecture | 8 | 2026-02-24 | Not Started |  | stripeService, paystackService, paymongoService all 878-1149 lines
T028 | Move CURRENT_YEAR to environment config | P2 | Architecture | 2 | 2026-02-24 | Not Started |  | Hardcoded '2025' in 3 files - will break next season
T029 | Centralize collection names in constants file | P2 | Architecture | 2 | 2026-02-24 | Not Started |  | Duplicated across location services
T030 | Extract Firebase initialization check to utility | P2 | Architecture | 3 | 2026-02-24 | Not Started |  | 14 duplicate 'Firebase db not initialized' checks
T031 | Add pagination to draft history API endpoints | P2 | Performance | 4 | 2026-02-24 | Not Started |  | pages/api/draft/submit-pick.ts - large JSON payloads
T032 | Memoize generateUniqueRankings() function | P2 | Performance | 2 | 2026-02-24 | Not Started |  | O(n log n) sort on every filter change
T033 | Cache countPositionsForParticipant() results | P2 | Performance | 2 | 2026-02-24 | Not Started |  | Called on every pick submission
T034 | Optimize ScrollingUsername animation in PicksBar | P3 | Performance | 2 | 2026-03-26 | Not Started |  | DOM reads trigger layout recalculations
T035 | Add jitter to Firebase retry logic | P3 | Performance | 1 | 2026-03-26 | Not Started |  | lib/firebase/firebaseAdapter.ts
T036 | Add circuit breaker metrics/logging | P3 | Architecture | 3 | 2026-03-26 | Not Started |  | No observable metrics of circuit breaker trips
T037 | Review and optimize image device sizes in next.config.js | P3 | Performance | 1 | 2026-03-26 | Not Started |  | Includes 3840px - may not be needed
T038 | Add TTL/version checking to localStorage queue caching | P3 | Architecture | 2 | 2026-03-26 | Not Started |  | useDraftQueue.ts - old queue data never expires

## Sprint Plan
Sprint | Duration | Focus Area | Tasks Included | Goal | Success Criteria
Sprint 1 | Week 1 | Performance Critical | T001-T008 | Eliminate largest performance blockers | All images < 500KB, draft room memoized
Sprint 2 | Week 2 | Code Quality Foundation | T009-T016 | Clean up debug code and type safety | Zero console.log in prod, 50% fewer any types
Sprint 3 | Week 3 | API & Caching | T017-T023 | Improve API performance | Cache headers on all endpoints, SWR deduplication
Sprint 4 | Week 4 | Architecture - Part 1 | T024-T027 | Break down large files | No files > 800 lines in core modules
Sprint 5 | Week 5 | Architecture - Part 2 | T028-T033 | Configuration & optimization | All config externalized, expensive computations cached
Sprint 6 | Backlog | Polish & Optimization | T034-T038 | Final improvements | All P3 items addressed

## Quick Reference
Quick Reference Commands
Task | Command | Notes
Find console statements | grep -r 'console\.' --include='*.ts' --include='*.tsx' ¦ wc -l | Run from project root
Find 'any' types | grep -rn ': any' --include='*.ts' --include='*.tsx' | Shows file:line:match
Find TODO/FIXME | grep -rn 'TODO\¦FIXME' --include='*.ts' --include='*.tsx' | Case sensitive
Convert PNG to WebP | cwebp -q 80 input.png -o output.webp | Quality 80 is good balance
Batch convert images | for f in *.png; do cwebp -q 80 "$f" -o "${f%.png}.webp"; done | Run in public/ folder
Find large files | find . -name '*.ts' -o -name '*.tsx' ¦ xargs wc -l ¦ sort -n ¦ tail -20 | Top 20 largest files
Check bundle size | npm run build && ls -la .next/static/chunks/ | After build
Run TypeScript check | npx tsc --noEmit | Type errors without building
Find files > 1000 lines | find . -name '*.ts' ¦ xargs wc -l ¦ awk '$1 > 1000' | Large file candidates